Overall Project Plan for the PROMASI Project

Version	Date	Author	Comment
0.1	22/10/2008	N. Petalidis	Initial version

# Project Overview
The PROMASI project aims at developing a project management simulator that will be used for the education of future software project managers. PROMASI should provide with a captivating gameplay of realistic scenarios aiming at becoming the educational tool of choice in software management courses.

For	Educational Institutions and Universities
Who	Have courses on Software Engineering and Software Project Management
The	PROMASI is a project management simulator with emphasis on software products
That	Allows for teaching different management scenarios in a multiplayer environment
Unlike	Current simulators that are single-player and with a difficult UI
Our product	Utilises open-source software to provide a flexible, generic and extensible platform for teaching project management through simulation.

The problem of	Successfully teaching project management concepts to students with little exposure to real life projects
Affects	Students
The impact of which is	Reduced learning
A successful solution would	Allow students to experiment with realistic scenarios and see the effect of their decisions to the project.

## Desired Outcomes
The following balanced scorecard describes the desired outcomes of the project.

## The Project Approach
The project should be organised as a semi-formal project using the Unified Process.

The project will be split into two streams

- Software Development (SD) – Development of software, building and integration
- Educational Courses Development (ED) – Development of courses and teaching material relating to the software simulator being build

The project is expected to take two years to complete. The project is to be staged with each stage taking between four and twelve months. Table X provides a summary of the planned stages. Each work stream will be baselined and synchronised on the stage boundaries.

Stage	Purpose	Key Deliverables	End Date
	Start of project
Initiation	Set up the project	Business Case / Overall Project Plans	15/11/2008
1 Demonstrate and pilot the new technology	Prove the overall project approach and then demonstrate and pilot the new platform	Demonstrable prototype / PROMASI Evolution 1: Platform pilot	1/02/2008
2 Develop and roll-out system	Develop fully working single player prototype / installed base increase	Educational course plans / PROMASI Evolution 2: / Single Player PROMASI	30/08/2008
3 Develop multi player system	MultiPlayer PROMASI available and launched	Educational course plans / PROMASI Evolution 3: / Multi Player PROMASI	30/08/2009
4 business as usual	System enhanced, installed base increased and problems addressed	Details to be added as earlier stages completed / Each stage will produce a new evolution of PROMASI	30/12/2009
Close Down	Conclude project and hand over all responsibilities to open-source community		01/02/2010

## Assumptions and constraints
The following assumptions were made in the construction of this plan:
- Enough personnel will be made available for development, testing and management of the project
- Enough technically able personnel can be found

## Evolution of the plan
Version	Milestone	Comment
1.0	End Of Stage 1	Signed off plan for Stage 2
2.0	End of Stage 2	Revised plan to cover Stage 3 and transition to business as usual
3.0	End of previous stage	The plan will be continuously revised throughout the project

Any minor revisions produced between these milestones will be point releases and will be version numbered accordingly.

# Project Organisation

Role	Primary Responsibilities	Secondary Responsibilities
Overall Project Manager	Overall Project Manager	QA Manager
Project Support	Project Office	Administrator
Software Development Manager	Work Stream Manager	Iteration Lead
Educational Course Development Manager	Work Stream Manager	Deputy to the Overall Project Manager
Software Architect	Architect	Technical Advisor to the management team
Development team	System and software development
Students/Lecturers	Provide direction on educational, quality and gameplay issues

# Project Review Authorities

Although no formal steering committee will be formed, the project will be reviewed regularly by a group of external reviewers

Reviewer	Responsibilities
TEI Serres, ICD Department (Sponsor)	Present in stage assessments, has control over budget and financial issues
A. Person	Provide advise on curricula and educational issues: invite to critical project reviews and support audits
B. Person	Provide technical governance: invite to critical project reviews and support audits

# Project Plan

Stage	Milestone	Assigned	Acceptance Criteria	Due Date
Initiation / Result: Project Underway	Project Approved Pre-work stream Project approved and commitment made / Work Streams Set up Pre-work stream Individual work streams set up, staffed and plans in place
Stage 1: Propose system architecture / Result: Selected approach proven	Model Specification Language agreed SW Dev Specification signed off by Reviewers / Basic Architecture Agreed SW Dev Demonstration of basic playing functionality with the toy models / Toy Models Developed EC Dev Demonstration of models in Vensim / Course Outline designed EC Dev Course plans, assignments, examination criteria signed off by Reviewers / Development infrastructure setup SW Dev Web site, CVS Server, Build Server, IDE Environment setup / Basic Concept proved SW Dev Demonstration of an implemented management scenario, signed off by Reviewers
Stage 2: Demonstrate and pilot the new technology / Result:Pilot commenced	UI Improved SW Dev UI with ability for project monitoring, personnel selection and project control / Core Engine Improved SW Dev Demonstration of ability to simulate incremental and iterative models / Personnel Engine Improved SW Dev Demonstration of ability to create own characters / Models Developed EC Dev Models of UP, XP, Waterfall processes demonstrated in Vensim / Students completed training EC Dev Students successfully pass exams in Optical Programming, OO Programming, SE1 and SE2 / Demonstrated at conference EC Dev Publication of results / Pilot commenced EC Dev Use of the simulator in classroom / Evolution 1 Available SW Dev Major release available in download site
Stage 3: Develop Multiplayer version / Result: Multiplayer version available.	Multiplayer capability added SW Dev Demonstration of ability for common marketplace and for players to compete against each other, / CMM For companies added SW Dev Demonstration of ability for companies to acquire experience and receive bonus for it / Technology successfully piloted EC Dev Simulator used with success in at least two courses / Sites Installed EC Dev Simulator in use in at least 2 different institutions / Group results available EC Dev Results from student's performance gathered / Satisfaction survey completed EC Dev Questionnaires completed by at least 20% of the users / Demonstrated at conference EC Dev Publication of results
Stage 4: Business as usual.	Milestones likely to be as show in plan. More details at a later stage of the project

# Estimates and Tolerances
Tolerances are established to define rules for identifying and escalating exceptions. Within these tolerances no action is required by the Reviewing Committee and the Overall Project Manager.
Type Of Milestone	Tolerance	Comments
End of Stage	10%overrun	Schedule slippage might affect other stages
End of Phase	10% scheduler overrun; no skipped iterations	If phase overruns, assess cause for slippage and adjust plans for next phase accordingly
End of Iteration	None	Iterations are strict time boxes. If iteration objectives are not met, then adjust subsequent iteration plans

# Management Strategy
The project is to be conducted in line with the Unified Process. An overview of the management strategy is provided by the following table.

Dimension	Decision
Style of delivery	Staged iterative and incremental delivery / Distributed team development / The SD stream will use the UP
Level of detail and formality	Low ceremony with high levels of user and stakeholder involvement / Adopt standard QA process
Reporting and communications	Primary reporting mechanism – stage and phase assessment supported by regular iterations or equivalent assessments / Management by exception
Product acceptance	Independent user acceptance and system test / Stakeholders involved in all iteration and phase reviews / Surveys trials and focus groups

# Project Monitoring and Control
The key elements of the strategy for monitoring and controlling the project
- Assessments and Reviews
- Regular Reporting

# Technical and Supporting Process Plans

A number of additional plans and supporting guideline documents are required

- CM Plan
- QA Plan

- User Interface Guidelines
- Programming Guidelines
- Logging Guidelines
- Modelling Guidelines
- Testing Guidelines